## Blad1
Legend
Task schould be around 90% by now
Do the task
Hard deadline
Collecting data to do task
|  |  | Weeks | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
Dates | time axis 2024-04-22 to 2024-06-16
|  |  | Days | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun | Mon | Tues | Wed | Thurs | Fri | Sat | Sun
Task | Person | Checker | Progess | 2024-04-22: PLAYTEST; 2024-05-13: PLAYTEST; 2024-05-27: PLAYTEST; 2024-06-10: project deadline
Playing Mechanic | Chris | May, Jesse | 0%
Guitar Minigame |  |  | 0% | bar: 2024-04-25 to 2024-05-05; 2024-05-12
Drum Minigame | TBA |  | 0% | bar: 2024-05-26
Mic Minigame | TBA |  | 0% | bar: 2024-05-26
Local Multiplayer | May | Chris, Jesse | 0% | bar: 2024-06-11
Controller Support |  |  | 0% | bar: 2024-05-04 to 2024-05-10; 2024-06-11
Multiple Players |  |  | 0% | bar: 2024-05-04 to 2024-05-12; 2024-06-11
Interaction between players |  |  | 0% | bar: 2024-05-04 to 2024-05-12; 2024-06-11
Point System | Jesse | Chris, May | 0% | bar: 2024-06-11
Brainstorm |  |  | 0% | bar: 2024-04-25; 2024-06-11
Implement in code |  |  | 0% | bar: 2024-04-25; 2024-05-11 to 2024-05-12; 2024-06-11
Implement in concept |  |  | 0% | bar: 2024-04-25; 2024-05-06 to 2024-05-12; 2024-06-11
Game Design | Everyone |  | 0% | bar: 2024-06-11
Implement Game phases |  |  | 0% | bar: 2024-05-26; 2024-06-11
Implement Instrument puicking |  |  | 0% | bar: 2024-05-26; 2024-06-11
Implement Band Leader |  |  | 0% | bar: 2024-05-26; 2024-06-11
Combat Extension |  |  | 0% | bar: 2024-06-11
Art for instruments |  |  | 0% | bar: 2024-06-11
Implement art |  |  | 0% | bar: 2024-06-11
FMOD Integration and Audio Design |  |  | 0% | bar: 2024-06-11
Compose soundtrack |  |  | 0% | bar: 2024-06-11
Compose SFX |  |  | 0% | bar: 2024-06-11
Implement into FMOD |  |  | 0% | bar: 2024-06-11
Implement into Unity |  |  | 0% | bar: 2024-06-11
Art Design |  |  | 0% | bar: 2024-06-11
Art for mutliple players |  |  | 0% | bar: 2024-05-05 to 2024-05-12; 2024-06-11
Add VFX for rendering |  |  | 0% | bar: 2024-06-10 to 2024-06-11
Create unique GUI for alll instruments |  |  | 0% | bar: 2024-05-05 to 2024-05-12; 2024-06-11
Create general GUI |  |  | 0% | bar: 2024-06-11
Cerate multiple maps |  |  | 0% | bar: 2024-06-11
Particle effects |  |  | 0% | bar: 2024-06-11
Cleanup |  |  | 0% | bar: 2024-06-11
documentatie |  |  | 0% | bar: 2024-06-02 to 2024-06-10
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
100%